## Activity Tracker
Day | SDD Stage | Planned Work (per assessment timeline) | Actual Work Summary | Est. Hrs | Actual Hrs | Actual Date | Key Artefacts | Status | Blockers / Open Items | Next Action
Day 1 | Discovery | Understand requirement + Discovery: business understanding, questions, assumptions, open decisions | Completed Day 1 Discovery & Requirement Analysis for the Employee Internal Transfer Digital Journey. Reviewed source-docs/Requirement for SDD.docx and authored BRD.md (BRD-001): business objective, primary actors (employee, manager, HR, and downstream Payroll/IT/Facilities/org-info stakeholders), the 8 journey stages, and the employee's explicit capabilities (select department/location/role, effective date, optional reason, submit, view status and pending actions). Separated what the source confirms as decided from what it leaves open, recording 11 open items (Q01-Q11: tenure, effective-date lead time, one-active-transfer limit, approval SLA, geographic scope, stakeholder assignment, failure/rollback behaviour, RBAC), plus explicit Business-vs-Technical decision sections, dependencies/integrations, authorization questions, and out-of-scope items. Updated project_context.md, constitution.md, and status.md for this project. | 2.5-3 | 3 | 2026-09-03 | BRD.md (BRD-001); project_context.md; constitution.md; status.md; .agent/rules/int-standards.laravel.md; .agent/rules/int-standards.nextjs.md | Complete | Q01-Q11 open in BRD.md; Q06/Q07/Q08/Q11 (stakeholder assignment, failure/rollback, RBAC) block Gate 1 readiness. No Laravel/Next.js codebase exists yet, so stack rule files are defaults pending scaffolding. | Get stakeholder decisions on the P0 open questions, then start Day 2 (BRD interpretation into initial .spec.md).
Day 2 | Specification | BRD interpretation + initial SDD specification | Authored the initial feature specification (specs/emp-internal-transfer.spec.md, Draft v1.0) from the approved Day 1 BRD-001: one-paragraph Intent, Context section, 17 Gherkin acceptance criteria (AC01-AC17) covering request initiation, validation/rejection, the eligibility gate, manager/HR approval transitions, downstream processing and completion, status/pending-action visibility, and authorization isolation. Added Explicitly Out of Scope, Non-Functional Constraints, and Frontend/Backend Responsibility Boundary sections, plus a full BRD-to-AC traceability table. Carried forward all of BRD-001's open items (Q01-Q11) without silently resolving any of them; confirmed auditability is not an approved constitution requirement and did not assert it as an AC. | 1-2 | 2 | 2026-09-04 | specs/emp-internal-transfer.spec.md (Draft v1.0) - Intent, Context, AC01-AC17, Out of Scope, NFRs, Frontend/Backend boundary, traceability | Complete | Q01-Q11 open in BRD.md, none resolved in the spec; API contract deliberately left as a Day 3 placeholder | Day 3: finalize API contract, exception tables, spec-derived unit test cases, and broader QA test cases
Day 3 | Specification | Acceptance Criteria + API Contract + spec-derived Test Cases | Finalized the specification for Gate 1: added the full API contract (API01 Create Transfer Request, API02 Get Transfer Details, API03 Approval/Stage Action) with request/response shapes, a status/pendingWith vocabulary, and per-endpoint exception tables; added a shared Error Contract envelope and a Next.js Consumption Contract section; flagged the base path, error envelope shape, and 403-vs-404 split as proposed decisions for Gate 1 rather than repository facts. Added UT01-UT17 mapped 1:1 to AC01-AC17 and extended traceability to the full BRD-to-AC-to-API-to-UT chain. Created test_cases/emp-internal-transfer.test_cases.md with 11 broader QA categories. Set spec status to In Peer Review (Gate 1). Also found and removed two more leftover Empty Floor artefacts missed on Day 1 (root CLAUDE.md, .agent/workflows/), and corrected an author-name recording error (Shamik Bhattacharya to Aditya Hazra) after catching a possible self-review risk before recording Sourav Kumar Maity as the Gate 1 reviewer. | 2 | 1 | 2026-09-08 | specs/emp-internal-transfer.spec.md (In Peer Review, Gate 1) - API01-API03, error contract, Next.js consumer contract, UT01-UT17, full traceability; test_cases/emp-internal-transfer.test_cases.md; CLAUDE.md and constitution.md corrected | Complete | Q01-Q11 still open, carried into Gate 1; 3 spec-level decisions (base path, error envelope, 403 vs 404) flagged for Gate 1 confirmation; Gate 1 reviewer assigned (Sourav Kumar Maity) but decision still pending | Await Sourav Kumar Maity's Gate 1 decision (Approved / Changes Requested); Day 5 Technical Plan once Approved
Day 4 | Gate 1 | Gate 1 peer review of the specification | Gate 1 peer review by Sourav Kumar Maity across five passes, with three revision cycles by the author. BRD and spec reviewed (PASS WITH CONDITIONS); v1.1 addressed all 15 observations (Q12/Q13 added, controlled assumptions for Q07/Q08, AC18/API04 downstream completion, state-model and AC12 fixes). BRD passed Gate 1; spec v1.1 re-review returned six consistency conditions, fixed in v1.2 (plus a self-caught UT12 fix and reviewer guidance). Part 4 returned nine mechanical items (P4-01..P4-09), fixed in v1.2.1 with a self-check against the reviewer's checklist. Final Part 5 review: spec APPROVED. | 1.5-2 | 2 | 2026-09-30 | BRD.md (Gate 1 PASS); specs/emp-internal-transfer.spec.md (Approved - Gate 1, v1.2.1) with review Parts 1-5 and revision notes v1.1, v1.2, v1.2.1; test_cases/emp-internal-transfer.test_cases.md updated for v1.2.1 | Complete | Carried into Day 5: open Q06/Q11/Q12/Q13; controlled assumptions Q05/Q07/Q08 to validate; contract gaps (pending_resolution entry, pendingWith with several steps, reference-data endpoints, downstream-role mapping); non-blocking editorial fix (Context Q01-Q11 count) | Day 5: Technical Plan + Architecture
Day 5 | Planning | Technical Plan + Architecture: integration approach, data model, failure handling, ADR candidates | Authored the technical plan from the Gate 1-approved spec: architecture and Laravel/Next.js responsibilities, API01-API04 mapping, logical data model, state model (hr_approved never persisted), auth/RBAC approach, reference-data options, downstream boundaries (human-completed via API04, no system integration), failure/concurrency/idempotency handling, security/observability/performance, testing strategy traced BRD-AC-API-UT, 11 ADR candidates and open decisions. No Laravel/Next.js source exists, so every choice is labelled Fact/Approved/Rule/Proposed/Open/ADR. Raised CR-01 (contradicting approved test cases AUTH-07/STATE-06/STATE-08), CR-02 (reference-data endpoint) and CR-03 (API01 idempotency). No code written. | 3-4 | 3 | 2026-09-30 | plans/emp-internal-transfer.plan.md (Draft - Technical Review Required); status.md; project_context.md; prompt_history.md | Complete - technical review pending | No technical reviewer assigned (R-01); ADR-0001 auth, ADR-0002 stack/DB/test frameworks, ADR-0004 role mapping undecided; CR-01 needs author + Gate 1 reviewer agreement; no Laravel/Next.js scaffold yet | Assign a technical reviewer and review the plan; decide ADR-0001/0002/0004 and CR-01; then Day 6: Task Decomposition + AI Prompts
Day 6 | Planning | Task Decomposition + AI Prompts: task-to-AC mapping, implementation prompts |  | 2.5-3 |  |  |  | Not Started
Day 7 | Implementation | Test-first implementation: RED tests + first implementation increment |  | 4-5 |  |  |  | Not Started
Day 8 | Implementation | Guided implementation: remaining core implementation + integration |  | 4-5 |  |  |  | Not Started
Day 9 | Validation | Validation + Security + Gate 2 preparation: GREEN tests, security review, traceability |  | 4-5 |  |  |  | Not Started
Day 10 | Gate 2 / Release | Gate 2 + final presentation: final artefact chain + demo |  | 2.5-3 |  |  |  | Not Started