## 10Day Timeline
Day | Activity | Expected Output | Effort | Actual Date | Actual Status | Evidence / Remarks | Status
Day 1 | Understand requirement + Discovery | Business understanding, questions, assumptions, open decisions | 2.5 hrs | 2026-08-26 | Complete | BRD.md, status.md, prompt_history.md — Full BRD-001 was created
Day 2 | BRD interpretation + SDD Spec | Initial SDD specification from BRD | 3 hrs | 2026-08-27 | Complete | specs/employee-internal-transfer.spec.md — Initial specification completed
Day 3 | Acceptance Criteria + API Contract + Test Cases | Acceptance Criteria, API Contract and Test Cases | 4 hrs | 2026-08-28 | Complete | specs/employee-internal-transfer.spec.md — AC, API and UT01–UT1; test_cases28
Day 4 | Gate 1 Peer Review | Gate 1 peer review and review comments | 1.5 hrs | 2026-08-29 | Not Started | Gate 1 review by Abhijit Adhikari is still pending
Day 5 | Technical Plan + Architecture | Technical Plan, Architecture, Data Model and Failure Handling | 3.5 hrs | 2026-08-30 | Partially Complete | Spec, AC, API and Test Cases completed; .plan.md is still pending
Day 6 | Task Decomposition + AI Prompts | Task decomposition and implementation prompts |  |  | Not started
Day 7 | Test-first implementation | RED tests + first implementation increment |  |  | Not started
Day 8 | Guided implementation | Core implementation and integration |  |  | Not started
Day 9 | Validation + Security + Gate 2 preparation | GREEN tests, security review, traceability |  |  | Not started
Day 10 | Gate 2 + Final Presentation | Gate 2 review and final presentation |  |  | Not started